## Slide 1: Factory Planning
Case Study
Summer 2024
Group 13
Group members
Aryan Sani Tourtchi 427611
Bibek Bhattacharyya 451926
Deven Paul 453329
Fidel Gatimu 442095
Saket Satyanarayan Totala 441801
Violeta Todorova 345680
Zishi Wang 451922
Christopher Kapella, M.Sc
Manuel Lauer, M.Sc
Notes: Laboratory for Machine Tools and Production Engineering of RWTH Aachen University
Chair of Production Engineering
Department of Factory Planning
Dr.-Ing. Matthias Dannapfel
Factory planning
Lecture 1
Introduction to Factory Planning & Project Management
Contact:
Niklas Schäfer
Laboratory for Machine Tools and Production Engineering WZL of RWTH Aachen University Campus-Boulevard 30
52074 Aachen Mail: N.Schaefer@wzl.rwth-aachen.de

## Slide 2: Content of the submission
Task 1 Executive Summary Page 3
Task 2 Factory Planning project plan Page 4
Task 3 Objectives and Strategic goals Page 5
Task 4 Plant Area Benchmark Page 6
Task 5 Site Selection Requirements Page 7
Task 6 Site Selection Page 8
Task 7 Process Planning Page 9
Task 8 Capacity Planning Page 10
Task 9 Factory Structure and Expansion Planning Page 11
Task 10 Next Steps Page 12

## Slide 3: Task 1 Executive summary Working Method, Key Results and Next Steps
2.Time: Factory construction is expected to start in 2024 and production is expected to begin in 2026.
4. Production, capacity and expansion planning:
Year 1: Capacity: 16.5 GWh
Planning production cars: 220,000
Planning production cells: 178,200,000
Year 10: Capacity: 42.174 GWh
Planning production cars: 562,222.22
Planning production cells: 455,400,000
01
02
03
04
1. Data Collection: Once your data needs have been identified, collect data from multiple sources, including web analysis, reviewing various survey research, and selecting appropriate data sources.
3. Site selection and reasons: Mangaluru, Karnataka, India.
due to:
- Highest overall score based on the criteria
- Meets technical requirments for production scalability
- Strong infrastructure and labor market
- Sufficient proximity to Tesla’s planned plant
05
5. Next steps:
- Start detailed engineering and procurement.
- Establish local supplier and logistics partnerships.
- Plan for phased implementation to start production within the specified month.

## Slide 4: Task 2 Factory planning project plan Gantt chart
FACTORY PLANNING PROJECT PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task | Project | Start | End | Duration | Owner | MAY |  |  | JUNE |  |  |  |  |  |  | JULY |  |  |  |  |  |  | AUGUST
 |  |  |  |  |  | 3 | 4 |  | 1 |  | 2 |  | 3 |  | 4 | 1 | 2 |  | 3 |  | 4 |  | 1
1 | Executive Summary | 9/6/2024 | 2/8/2024 | 25 | Zishi & Deven |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Factory Planning Project Plan | 20/5/2024 | 28/6/2024 | 40 | Zishi & Deven |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Objectives & Strategy goals | 24/5/2024 | 2/7/2024 | 40 | Zishi |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Plant Area Benchmark | 22/6/2024 | 28/7/2024 | 30 | Violeta |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Site Selection Requirements | 20/5/2024 | 5/7/2024 | 45 | Fidel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
6 | Site Selection | 14/6/2024 | 24/7/2024 | 40 | Fidel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
7 | Process Planning | 20/5/2024 | 30/7/2024 | 70 | Aryan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
8 | Capacity Planning | 9/6/2024 | 14/7/2024 | 35 | Bibek |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
9 | Factory Structure & Expansion Planning | 9/6/2024 | 29/7/2024 | 50 | Saket & Bibek |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
10 | Next Steps | 12/6/2024 | 17/7/2024 | 35 | Deven |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
11 | Submission | 2/7/2024 | 2/8/2024 | 30 | ALL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
12 | Final Presentation | 29/7/2024 | 6/8/2024 | 8 | ALL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
= Review
= Project Work

## Slide 5: Task 3 Objectives and strategic goals Strategic objectives of our factory
Requirement:
Objectives:
Year 1:
Required Plant capacity : 15 GWh
Planning production cars: 220,000
Planning production cells: 178,200,000
Year 10:
Required Plant capacity: 38.34 GWh
Planning production cars: 56,222.2
Planning production cells: 455,400,000
1. Time: Factory construction is expected to start in 2024 and production is expected to begin in 2026.
2. Reliability and Quality: Maintain high standards of quality and reliability in battery cell production to support Tesla’s reputation for excellence.
3. Sustainability: Ensure environmentally friendly production processes to align with Tesla’s sustainability commitments.

## Slide 6: Task 4 Plant area benchmark Production Output Calculation
Area Requirement and Evaluation for New Tesla Battery Production Plant
Recommended Location: Mangaluru, Karnataka, India
Plant | Area (m²) | Production Capacity (GWh/year) | Area per GWh (m²/GWh)
Tesla Gigafactory Nevada | 492,000 | 35 | 14,057
LG Chem Ochang Plant | 93,000 | 9 | 10,333
CATL Ningde Plant | 325,000 | 35 | 9,286
Average |  |  | 11,225
Benchmark Analysis:
Year | Production Output (GWh) | Area Required (m²)
Year One | 10 | 112,250
Year Ten | 100 | 1,122,500
Production Output Estimates:
Location | Size (m²) | Price (US$) | Distance to Bangalore (km) | Distance to Airport (km) | Distance to Seaport (km) | City Population | Suitability
Bangalore | 200,000 | 36,000,000 | - | 45 | 330 | 12.3 million | Insufficient area for long-term expansion
Hubli-Dharwar | 245,000 | 29,000,000 | 440 | 30 | 170 | 950,000 | Insufficient area for long-term expansion
Mangaluru | 300,000 | 28,000,000 | 360 | 17 | 9 | 480,000 | Best option for long-term expansion
Location Evaluation:

## Slide 7: Task 5 Site Selection Requirements Key Criteria and Justifications
Sources: Justification in Back up slides
  Excellent transport links and reliable utilities
  Availability of qualified personnel
  Sufficient space for future expansion and flexibility of site layout
  Affordable cost of land and workers
  Within a 200km radius close to Tesla’s planned factory
  Sufficient supply network of energy and useful supplies such as water
Pair-by-pair comparison Evaluation criteria -1 Less important 0 Equally important 1 More important | Employee qualification | Expansion options | Transport connection and infrastructure | Cost of land and workers | Proximity to Tesla’s planned factory | Supply network | Sum
Employee qualification | X | -1 | -1 | -1 | -1 | -1 | -5
Expansion options | 1 | X | 0 | -1 | -1 | -1 | -2
Transport connection and infrastructure | 1 | 1 | X | -1 | -1 | -1 | -1
Cost of land and workers | 1 | 0 | 1 | X | 0 | -1 | 1
Proximity to Tesla’s planned factory | -1 | -1 | 1 | -1 | X | 1 | -1
Supply network | 1 | 1 | 1 | 1 | 1 | X | 5
The following are the factors used in the pair by pair comparison

## Slide 8: Task 6 Site Selection Evaluation of Pre-Selected Locations
 | Weighting | Bangalore |  | Hubli-Dharwar |  | Mangaluru | 
Criteria |  | DoF | value | DoF | value | DoF | value
Employee qualifications | 3 | 5 Aerospace, IT, Biotech. 3 universities | 15 | 5 Automotive, electrical, etc. 2 Universities | 15 | 5 Chemical,textile,etc.1 uni & Many colleges | 15
Expansion options | 12 | 2 Bad | 24 | 4 Good | 48 | 5 Best | 60
Transport connection and infrastructure | 15 | 5 Bus station < 400m Highway < 300m Airport: 45km | 75 | 3 Airport: 440km Seaport: 170km Highway < 2km | 45 | 4 Highway<2km Airport: 17km Seaport: 9km | 60
Cost of land and workers | 21 | 2 36,000,000$ | 42 | 4 25,000,000$ | 84 | 3 29,000,000$ | 63
Proximity to Tesla’s planned plant | 16 | 5 Best | 80 | 4 Good | 64 | 4 Good | 64
Supply network | 33 | 4 Good | 132 | 4 Good | 132 | 4 Good | 132
Total value |  |  | 368 |  | 388 |  | 394

## Slide 9: Task 7 Process planning Technology Chain & Machine Usage
Sources: 1 Study by the PEM of RWTH Aachen University, 2 Masterdokument_Zellherstellung_v63 Vordruckfreigabe.pptx, 3 E-Mail by the CEO
Electrode manufacturing
Cell assembly
Cell finishing
Mixing & Dispersing
Process: Mixing active materials, conductive additives, solvents, and binders to form a homogeneous slurry
Machines: Intensive mixers with vacuum and temperature control systems
Coating
Process: Applying the slurry onto a current collector foil (aluminum for cathode, copper for anode)
Technologies: Slot-die coating, curtain coating
Drying & Calendering
Process: Drying the coated foils and compressing them to the desired thickness and density
Machines: Industrial drying ovens, calendering machines
Technology: Dry mixing, wet mixing under vacuum to avoid gas inclusions
Machines: Coating machines with precise control for thickness and uniformity
Technologies: Laser drying, extrusion for uniform thickness
Cutting & Stacking
Process: Cutting electrodes and separators to size and stacking them in the correct sequence
Machines: Laser cutting machines, stacking machines
Winding
Process: Winding electrode and separator foils into a cylindrical or prismatic shape (for cylindrical and prismatic cells)
Machines: Winding machines
Electrolyte Filling
Process: Filling the cells with electrolyte under vacuum and ensuring thorough wetting
Machines: Electrolyte filling machines with high-precision dosing systems
Sealing
Machines: Sealing machines (heat sealing, ultrasonic welding
Process: Sealing the cells to ensure airtight containment of the electrolyte
Technologies: Laser cutting, lamination of the separator
Technologies: Automated winding systems with tension control
Technologies: Vacuum filling, pressure profile application for wetting
Technologies: Laser welding for prismatic cells, heat sealing for pouch cells
Formation
Process: Charging and discharging cells to form the solid electrolyte interphase (SEI) layer
Machines: Formation chambers with precise control over temperature and current
Aging & Testing
Process: Aging cells at elevated temperatures and performing quality assurance tests
Technologies: High-temperature aging, open circuit voltage (OCV) measurements
Final Inspection & Packaging
Process: Final quality inspections and packaging for shipment
Machines Required: Inspection systems, automated packaging lines
Technologies: Controlled atmosphere formation chambers
Machines: Aging chambers, testing rigs for electrical performance
Technologies: Visual inspection systems, automated packaging solutions

## Slide 10
Task 8 Capacity Planning Capacity Requirement and Floor Area Planning for Year 1 and Year 10 w.r.t Production Process.
Sources 1: Technology research (Company-internal documents); Source 2: Backup Slide; Aging Center height: https://www.belltestchamber.com/battery-test-chamber/double-deck-burn-in-chamber-for-battery-test-aging-test-chamber.html
1st Year target capacity: 15 GWh.
1st Year Maximum capacity: 16.5 GWh.(10% Buffer)
Annual demand growth rate of 9.81% considered.
10th Year target capacity: 38.34 GWh.
10th Year Maximum capacity: 42.17 GWh.(10% Buffer)
3 shift/day @7.5hrs shift for 298 Days.
Electrode Manufacturing consists of 6 subprocesses.
Targets & Assumptions
Electrode Manufacturing
Cell
Assembly
Cell
Finishing
Key Processes
Year 1
Year 10
Total Area: 4805 m2
Total Number of Machines: 101
Total Area: 2550 m2
Total Capacity: 50,000 cell/hr/day
Total Area: 1312 m2
Total Capacity: 1,782,000 cell/hr/day
Total Area: 13,817 m2
Total Number of Machines: 348
Total Area: 5100 m2
Total Capacity: 100,000 cell/hr/day
Total Area: 3353 m2
Total Capacity: 4,554,792 cell/hr/day
Cumulative Floor Space
Total Area: 22,270 m2
Total Area: 8,667 m2
Cell Assembly process fully automatic
Preoptimizations to 50,000 cell/hr/day.
Includes 4 sub-processes.
Scaling up on longer axis for increased production.
Cell Finishing with automatic testing
Customized supplier’s solution for type 4680.
Aging Rack Volume(1.0m x 0.46m x 0.13m )= 0.05 m3
15 Racks in 1 Ageing Centre @ 75 Cells per Rack.
Aging Centre Dimension: 1.0m x 0.46m x 2.0m

## Slide 11
Sources: 1) Mail by the CEO 2) General assumptions 3) Backup slide
Key design features:
Separate entry and exit gates for personnel and materials.
The layout will feature a double-lane road throughout.
Task 9 Factory Structure and Expansion Planning Factory Structure Designed Optimally for Current Production and Future Expansion.
Remarks for expansion:
Ample parking space will be available for both employees and material trucks to prevent in-plant traffic.
Construction in the expansion area will proceed without impacting the existing production schedule or material flow.
Exit gate for personnel(All)
Personnel Gate
(Factory Staff)
Material Gate
Inbound storage
Truck parking
Exit Gate For Trucks
Utility & Storage Expansion
Outbound storage
W & E
Personnel Parking
Administration
Cafeteria
Roads
Roads
Roads
Roads
Road
Cafeteria Expansion
Road
Personnel Gate (Administration)
Security
Fire safety and training
SCM (Supply chain management)
Energy
Water and Effluent treatment
Occupational health and safety
400m
Production
Expansion
Cell Finishing/
Ageing 2041 m2
Cell Assembly
(4 Sub Processes)
2550 m2
Cell Manufacturing
(6 Sub Processes)
9312 m2
Outbound
Storage
Road
Parking Expansion
Maintenance
Maintenance
Road
Production
Area
Cell Finishing/
Ageing 1312 m2
Cell Manufacturing
(6 Sub Processes)
4505 m2
Cell Assembly
(4 Sub Processes)
2550 m2

## Slide 12: Task 10 Next Steps Multi-stage Expansion Strategy to Ensure Delivery for Growing Market Needs
Multi-stage expansion strategy
Stage 1 – 2026
Stage 2 – 2031
Stage 3 – 2036
Possible Stage 4 – Multi-plant augmentation
Chart: Plant Capacity in GWh
| 2026 | 2031 | 2036 | 2041-204x
Required | 15 | 26.67 | 38.33 | 45
Actual | 16.5 | 29.34 | 42.17 | 52.71
Production augmentation in existing facility by 25% in Stage 2
Addition of new production facility in Stage
Key expansion Areas
Sources: 1. E-mail from CEO, 2. https://www.statista.com/outlook/mmo/electric-vehicles/worldwide : The Electric Vehicles market worldwide is projected to grow by 9.82% (2024-2028) , 3. Explanation in backup
Procurement of land for site, legal signings and partnerships for raw-material
Phase-implementation to start production as soon as possible
Next Steps

## Slide 13: Task 1 Executive summary Enter title here
BACKUP

## Slide 14: Task 2 Factory planning project plan Enter title here
BACKUP

## Slide 15: Task 3 Objectives and strategic goals Enter title here
BACKUP

## Slide 16: Task 4 Plant Area Benchmarks Enter title here
BACKUP

## Slide 17: Task 5 Site Selection Requirements Factors Justification
Sources:1.lecture Slides L3_Location planning and plant structure planning 2.Case of company-internal documents
BACKUP
Criteria | Justification
Employee Qualification | Availability of qualified employees ensures hiring of qualified personnel who are critical for the efficient operations of the company
Expansion options | Expansion options are crucial for a factory to meet its future-projected increased demands
Transport connection and infrastructure | Choosing a location hinges significantly on transport connections, which are vital for ensuring accessibility, expanding reach and optimizing logistical operations
Proximity to Tesla’s planned factory | Proximity to the Tesla’s planned factory ensures a continuous supply of materials and a more efficient operations with less down times.
Supply network | Having a sufficient supply network of amenities such as energy and water ensures the factory runs efficiently and maintains a more sustainable operation

## Slide 18: Task 6 Site Selection Pair-by-pair comparison
Sources:1.lecture Slides L3_Location planning and plant structure planning 2.Case of company-internal documents
BACKUP
Pair-by-pair comparison Evaluation criteria -1 Less important 0 Equally important 1 More important | Employee qualification | Expansion options | Transport connection and infrastructure | Cost of land and workers | Proximity to Tesla’s planned factory | Supply network | Sum | Standardization summand | Absolute weighting | Standardization weighting
Employee qualification | X | -1 | -1 | -1 | -1 | -1 | -5 | 6 | 1 | 3
Expansion options | 1 | X | 0 | -1 | -1 | -1 | -2 | 6 | 4 | 12
Transport connection and infrastructure | 1 | 1 | X | -1 | -1 | -1 | -1 | 6 | 5 | 15
Cost of land and workers | 1 | 0 | 1 | X | 0 | -1 | 1 | 6 | 7 | 21
Proximity to Tesla’s planned factory | -1 | -1 | 1 | -1 | X | 1 | -1 | 6 | 5 | 16
Supply network | 1 | 1 | 1 | 1 | 1 | X | 5 | 6 | 1 | 33

## Slide 19: Task 6 Site Selection Comparison of the 3 Pre-Selected Cities
Sources:1.lecture Slides L3_Location planning and plant structure planning 2.Case of company-internal documents
BACKUP
 | Weighting | Bangalore |  | Hubli-Dharwar |  | Mangaluru | 
Criteria |  | DoF | value | DoF | value | DoF | value
Employee qualifications | 3 | 5 | 15 | 5 | 15 | 5 | 15
Expansion options | 12 | 2 | 24 | 4 | 48 | 5 | 60
Transport connection and infrastructure | 15 | 5 | 75 | 3 | 45 | 4 | 60
Cost of land and workers | 21 | 2 | 42 | 4 | 84 | 3 | 63
Proximity to Tesla’s planned plant | 16 | 5 | 80 | 4 | 64 | 4 | 64
Supply network | 33 | 4 | 132 | 4 | 132 | 4 | 132
Total value |  |  | 368 |  | 388 |  | 394
Sources:1.lecture Slides L3_Location planning and plant structure planning 2.Case of company-internal documents

## Slide 20: Task 7 Process Planning Assumptions & Justification
BACKUP
Justification:
  Mixing and Dispersing: Ensures homogeneous slurry critical for electrode performance
  Coating and Drying: Accurate coating and drying to maintain electrode integrity
  Cutting, Stacking, and Winding: Essential for creating the cell's core structure
  Electrolyte Filling and Sealing: Critical for cell's electrochemical performance
  Formation, Aging, and Testing: Ensures reliability and longevity of the battery cells
Assumptions:
  Standard manufacturing processes based on industry norms
  Emphasis on precision and control to ensure high-quality output

## Slide 21: Task 8 Capacity Planning Capacity Requirement and Floor Area Planning for Year 1 and Year 10 w.r.t Production Process.
Source 1: https://shorturl.at/4laaX ;Source 2: https://batteryuniversity.com/ Source 3: https://www.batterydesign.net/tesla-4680-cell/ , Source 4: https://www.youtube.com/watch?v=aCz6BZnf35c&t=218s , Source 5: https://www.statista.com/outlook/mmo/electric-vehicles/worldwide
BACKUP
Year 1
Year 10
Equipment | Production Output (GWh/unit/year) | No. of units | Machine area x (m2) | Non-Func Area y (m2) | Total Area* used (x+y) (m2)
DP Vacuum mixer | 0.4 (OEE = 80%) = 0.32 | 52 | 520 | 364 | 884
Electrode Coating machine (ECM) | 3.5 | 5 | 600 | 420 | 1,020
Drying Machine | w.r.t ECM | 5 | 1,125 | 787.5 | 1,912.5
Calander machine | w.r.t ECM | 2 | 232 | 162.4 | 394.4
Laser cutting machine | w.r.t ECM | 1 | 35 | 24.5 | 59.5
Vacuum Drying machine | w.r.t ECM | 35 | 315 | 220.5 | 535.5
Production Step 1: Electrode Manufacturing (Annually)
Equipment | Production Output (GWh/unit/year) | No. of units | Machine area x (m2) | Non-Func Area y (m2) | Total Area* used (x+y) (m2)
DP Vacuum mixer | 0.4 (OEE = 80%) = 0.32 | 132 | 1,320 | 924 | 2,244
Electrode Coating machine (ECM) | 3.5 | 13 | 1,560 | 1,092 | 2,652
Drying Machine | w.r.t ECM | 13 | 2,925 | 2,047.5 | 4,972.5
Calander machine | w.r.t ECM | 5 | 580 | 406 | 986
Laser cutting machine | w.r.t ECM | 3 | 105 | 73.5 | 178.5
Vacuum Drying machine | w.r.t ECM | 182 | 1,638 | 1,146.6 | 2,784.6
Production Step 2: Cell Assembly (Annually)
Maximum Production | Required Production | Maximum capacity (GWh/year) | Total area*​ (m2)
178,200,000 Cells | 162,000,000 (15 GWh) | 16.5 | 2,550
Maximum Production | Required Production | Maximum capacity (GWh/year) | Total area*​ (m2)
455,479,200 Cells | 414,000,000 (15 GWh) | 38.34 | 5,100
Production Step 3: Cell Finishing (Annually)
Specifications |  | Total Area (m2)
Aging – (3 days delay = 100 Working days) | 1,s782,000 cell/day | 1,312
Total No of Aging Center and Area(Z) | 1,584 & 729 m2 | 
Testing towers(0.30*Z) + Automatic Transport(0.50*Z) | 583 m2 | 
Specifications |  | Total Area (m2)
Aging – (3 days delay = 100 Working days) | 4,554,792 cell/day | 3,353
Total No of Aging Center and Area(Z) | 4,049 & 1,863 m2 | 
Testing towers(0.30*Z) + Automatic Transport(0.50*Z) | 1,490 m2 | 
* Machine + Non-functional area(70% of Machine area); Non-Functional area: temporary Storage + Logistic + Maintenance
Total 298 Working Days: 365 – 52 Sundays – 15 Public Holidays.
Expected Demand in 10 years = 200,000*(1+0.098)^10
Notes: References:
https://www.indialawoffices.com/legal-articles/work-hours-and-office-timing-in-india -10-12 Hrs per day of factory operations
https://www.batterydesign.net/tesla-4680-cell/#:~:text=26.5Ah%20(estimate%20based%20on,Ah%20at%20C%2F20%20charge : Capacity of 4680 Battery. 26.5Ah
https://www.batterydesign.net/tesla-4680-cell/ 3.7V
https://day-off.app/2024/01/11/how-many-workdays-are-there-in-a-year/#:~:text=India%3A,6%20days%20%E2%80%93%2015%20holidays). 365-52sundays-15 holidays=298 Days
https://energy.economictimes.indiatimes.com/news/power/indias-ev-revolution-dashboard-predicts-45-5-cagr-1-6-crore-evs-by-2030/104471821 CAGR 45.5%
https://www.statista.com/outlook/mmo/electric-vehicles/worldwide : The Electric Vehicles market worldwide is projected to grow by 9.82% (2024-2028) resulting in a market volume of US$906.7bn in 2028 https://www.reddit.com/r/teslamotors/comments/1bjku12/tesla_produces_nearly_14_million_4680_cells_in_a/ Tesla Produces 1.4M 4680 cell in a week.
https://www.youtube.com/watch?v=aCz6BZnf35c&t=218s Additonal space requirement, temporary storeage, transportation, Misclaneious(30+30+10)
https://iopscience.iop.org/article/10.1149/1945-7111/ad14d0#:~:text=The%204680%20cell%20format%20(46,and%20a%20%22tabless%22%20design. Cell dimension 40dia *80long
https://batteryuniversity.com/ shelf and battery dimsnion
https://www.tek.com/en/blog/forming-the-best-solution-for-battery-formation-and-aging Area for EOL
https://www.pem.rwth-aachen.de/global/show_document.asp?id=aaaaaaaaabdqbtk Process Layout RWTH

## Slide 22: Task 9 Factory Structure and Expansion Planning Optimized Material and Personnel Flow via Efficient Central Type Factory Structure.
Plant capacity in GWh | 15 | 16.5
Administration, procurement, sales etc. (white collar jobs) : 30% of total | 675 | 742
Factory employees, technicians, etc. (blue collar jobs): 70% of total | 1,575 | 1,733
Total (@150 people/GWh) | 2,250 | 2,475
Personnel Figures
BACKUP
Production step | Total Area ()
Electrode manufacturing | 4,805.9
Cell Assembly | 2,550
Cell finishing | 1,312
Total | 8,667.9
Production step | 
Electrode manufacturing | 4,805.9
Cell Assembly | 2,550
Cell finishing | 1,312
Total | 8,667.9
Storage | At 15.0 GWh capacity | At 16.5 GWh capacity
Raw material (Inbound) | 2,520 | 2,772
Dispatch (Outbound) | 2,520 | 2,772
Department​ | Area required ()​ | Area()​
Administration​ offices and conference rooms | (7 + 2) / person | 2,025
SCM​ | 1,200 – 1,300 | 1,250
Energy​ | 2,500 | 2,500
Parking​ | 1.35 parking space/100 m2 | 3,300
Security​ | 15 * 20 /gate | 1,200​
Fire Safety and training​ | 2,500 | 2,500
Cafeteria​ + Break room (75% of people) | 1.25 / per person | 2,320
Waste and Effluent Treatment​ | 2,500 | 2,500
Department​ |  | 
Administration​ offices and conference rooms | (7 + 2) / person | 2,025
SCM​ | 1,200 – 1,300 | 1,250
Energy​ | 2,500 | 2,500
Parking​ | 1.35 parking space/100 m2 | 3,300
Security​ | 15 * 20 /gate | 1,200​
Fire Safety and training​ | 2,500 | 2,500
Cafeteria​ + Break room (75% of people) | 1.25 / per person | 2,320
Waste and Effluent Treatment​ | 2,500 | 2,500
Factory Sub Structures
Production Line
Storage
Sources: 1. Number of jobs per GWh, 2. Type of jobs, 3. Office space requirements 4. Canteen requirements 5. Production facility of battery manufacturing 6. Parking space required 7. Standard parking space 8. General Assumptions

## Slide 23: Task 10 Next Steps Expansion plan incremental market demand
Sources: 1. Technology research (company-internal document), 2. Capacity_Planning_and_Expansion (Attached Excel) ~ Own Estimation
BACKUP
Year  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Planned production of cars | 220,000 | 254,222.2 | 288,444.4 | 322,666.67 | 356,888.9 | 391,111.1 | 425,333.3 | 459,555.6 | 493,777.8 | 528,000 | 562,222.2
Planned production of Cells | 178,200,000 | 205,920,000 | 233,640,000 | 261,360,000 | 289,080,000 | 316,800,000 | 344,520,000 | 372,240,000 | 399,960,000 | 427,680,000 | 455,400,000
Required/Actual GWh | 15(16.5) | 17.3(19.67) | 19.6(21.6) | 22(24.2) | 24.3(26.7) | 26.67(29.3) | 29(31.9) | 31.3(34.67) | 33.6(37.3) | 36(39.6) | 38.3(42.17)
Stage 1
Stage 2
Stage 3
Multi-Stage Expansion plan
Machine type | Number of machines | Total Functional Area(m2) | Machine Area Non-Functional
DP Vacuum mixer | 132 | 1320 | 924
Electrode Coating machine | 13 | 1560 | 1092
Drying Machine | 13 | 2925 | 2047.5
Calender machine | 5 | 580 | 406
Laser cutting machine | 3 | 105 | 73.5
Vacuum Drying machine | 182 | 1638 | 1146.6
Cell assembly | 2 | 3000 | 2100
Cell Finishing | 1 | - | 8070
Machine type | Number of machines | Total Functional Area(m2) | Machine Area Non-Functional
DP Vacuum mixer | 52 | 520 | 364
Electrode Coating machine | 5 | 600 | 420
Drying Machine | 5 | 1125 | 787.5
Calender machine | 2 | 232 | 162.4
Laser cutting machine | 1 | 35 | 24.5
Vacuum Drying machine | 35 | 315 | 220.5
Cell assembly | 1 | 1500 | 1050
Cell Finishing | 1 | - | 8070
Machine type | Number of machines | Total Functional Area(m2) | Machine Area Non-Functional
DP Vacuum mixer | 100 | 1000 | 700
Electrode Coating machine | 8 | 960 | 672
Drying Machine | 8 | 1800 | 1404
Calender machine | 3 | 348 | 243.6
Laser cutting machine | 2 | 70 | 49
Vacuum Drying machine | 123 | 1107 | 772.4
Cell assembly | 1 | 1500 | 1050
Cell Finishing | 1 | - | 8070